## Inherent Risk Register
Vendor Risk Register — Inherent Risk
Vendor: CloudVault Data Solutions ¦ Assessment Date: 2026-03-05 ¦ Methodology: Likelihood (1-5) x Impact (1-5)
Finding ID | Domain | Finding Title | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Rating | Data Sensitivity | Owner (Vendor Side) | Target Remediation (Days)
F-01 | Access Control | MFA not mandatory for standard end-user accounts | 4 | 5 | 20 | Critical | Confidential PII/Financial | VP Engineering | 45
F-02 | Network Security | Penetration test exceeds 12-month cadence (15 months) | 3 | 4 | 12 | High | Confidential PII/Financial | CISO | 60
F-03 | Governance | SOC 2 exception: untimely access revocation (3 sampled users) | 3 | 3 | 9 | Medium | Confidential PII/Financial | IT Operations | 60
F-04 | Access Control | Manual deprovisioning SLA adherence gap (legacy/contractor accounts) | 3 | 3 | 9 | Medium | Confidential PII/Financial | IT Operations | 60
F-05 | Business Continuity | DR full failover test exceeds 12-month cadence (18 months) | 3 | 4 | 12 | High | Confidential PII/Financial | Head of Infrastructure | 90
F-06 | Data Security | DLP not implemented at application layer | 2 | 4 | 8 | Medium | Confidential PII/Financial | CISO | 120
F-07 | Fourth-Party Risk | Subprocessor due-diligence process not formalized | 2 | 2 | 4 | Low | Confidential PII/Financial | Director of Compliance | 90
F-08 | Application Security | No formal SLA for Medium/Low vulnerability remediation | 2 | 2 | 4 | Low | Confidential PII/Financial | Head of Engineering | 90
F-09 | Data Security | Customer-managed encryption keys (BYOK) unavailable | 1 | 3 | 3 | Low | Confidential PII/Financial | Product Management | 270
Summary by Rating
Rating | Count
Critical | 1
High | 2
Medium | 3
Low | 3