## Residual Risk Register
Vendor Risk Register — Inherent vs. Residual Risk
Vendor: CloudVault Data Solutions ¦ Residual Assessment Date: 2026-07-15
Finding ID | Finding Title | CAP Status | Inh. Likelihood | Inh. Impact | Inherent Score | Inherent Rating | Res. Likelihood | Res. Impact | Residual Score | Residual Rating | Risk Reduction
F-01 | MFA not mandatory for standard end-user accounts | Closed | 4 | 5 | 20 | Critical | 1 | 2 | 2 | Low | 90%
F-02 | Penetration test exceeds 12-month cadence | Closed | 3 | 4 | 12 | High | 1 | 2 | 2 | Low | 83.33%
F-03 | SOC 2 exception: untimely access revocation | Closed | 3 | 3 | 9 | Medium | 1 | 2 | 2 | Low | 77.78%
F-04 | Manual deprovisioning SLA adherence gap | Closed | 3 | 3 | 9 | Medium | 1 | 2 | 2 | Low | 77.78%
F-05 | DR full failover test exceeds cadence | Closed | 3 | 4 | 12 | High | 1 | 2 | 2 | Low | 83.33%
F-06 | DLP not implemented at application layer | In Progress | 2 | 4 | 8 | Medium | 2 | 3 | 6 | Medium | 25%
F-07 | Subprocessor due-diligence not formalized | Closed | 2 | 2 | 4 | Low | 1 | 1 | 1 | Low | 75%
F-08 | No formal SLA for Medium/Low vulnerabilities | Closed | 2 | 2 | 4 | Low | 1 | 1 | 1 | Low | 75%
F-09 | Customer-managed encryption keys (BYOK) unavailable | Monitoring (no CAP) | 1 | 3 | 3 | Low | 1 | 3 | 3 | Low | 0%
| TOTAL (sum of scores) |  |  |  | 81 |  |  |  | 21 |  | 74.07%